## 기능 목록
카테고리 | 기능명 | API 엔드포인트 | Backend | UI | 비동기 Job | 비고/체크사항
인증 | 로그인 | POST /api/auth/login | ✅ | ✅ | - | JWT + RefreshToken 발급
| 로그아웃 | POST /api/auth/logout | ✅ | ✅ | - | AccessToken 블랙리스트 등록
| 회원가입 | POST /api/auth/register | ✅ | ✅ | - | AUTH_REGISTRATION_ENABLED=true 시 활성화
| 토큰 갱신 | POST /api/auth/refresh | ✅ | ✅ | - | RefreshToken 로테이션 + 재사용 감지
사용자 계정 | 내 정보 조회 | GET /api/user | ✅ | ✅ | -
| 환경설정 조회 | GET /api/user/preferences | ✅ | ✅ | -
| 환경설정 수정 | PUT /api/user/preferences | ✅ | ✅ | - | 테마, 언어 등
| 비밀번호 변경 | POST /api/user/credential | ✅ | ✅ | -
| 계정 삭제 | DELETE /api/user/account | ✅ | ✅ | -
호스트 관리 | 호스트 목록 조회 | GET /api/host | ✅ | ✅ | - | 그룹별 트리 구조
| 호스트 추가 | POST /api/host | ✅ | ✅ | -
| 호스트 수정 | PUT /api/host/:hostUid | ✅ | ✅ | -
| 호스트 삭제 | DELETE /api/host/:hostUid | ✅ | ✅ | -
| 호스트 그룹 이동 | POST /api/host/:hostUid/move | ✅ | ✅ | - | DnD 지원
| 그룹 생성 | POST /api/host/group | ✅ | ✅ | -
| 그룹 수정 | PUT /api/host/group/:groupId | ✅ | ✅ | -
| 그룹 삭제 | DELETE /api/host/group/:groupId | ✅ | ✅ | -
| CMS 로그인 | POST /api/:hostUid/cms-auth/login | ✅ | ✅ | - | HA 자동 감지 포함
| 레거시 XML 가져오기 | (프론트 파싱) | - | ✅ | - | CUBRID Admin XML import
DB 라이프사이클 | DB 목록/상태 조회 | GET /api/:hostUid/database/start-info | ✅ | ✅ | -
| DB 시작 | POST /api/:hostUid/database/start/:dbname | ✅ | ✅ | - | HA DB는 ha_start 사용
| DB 중지 | POST /api/:hostUid/database/stop/:dbname | ✅ | ✅ | - | HA DB는 ha_stop 사용
| DB 재시작 | POST /api/:hostUid/database/restart/:dbname | ✅ | ✅ | -
| DB 생성 | POST /api/:hostUid/database/create | ✅ | ✅ | ✅ | 비동기 job / auto-start, user, addvol 옵션
| DB 삭제 | DELETE /api/:hostUid/database/:dbname | ✅ | ✅ | -
| DB 생성 기본정보 | GET /api/:hostUid/database/create-info | ✅ | ✅ | -
| 볼륨 정보 조회 | GET /api/:hostUid/database/volume-info/:dbname | ✅ | ✅ | -
DB 관리 | DB 복사 | POST /api/:hostUid/database/copy | ✅ | ✅ | ✅ | 비동기 job
| DB 이름 변경 | POST /api/:hostUid/database/rename/:dbname | ✅ | ✅ | ✅ | 비동기 job
| DB 언로드 | POST /api/:hostUid/database/unload/:dbname | ✅ | ✅ | ✅ | 비동기 job / 최대 12시간
| 언로드 정보 조회 | GET /api/:hostUid/database/unload-info | ✅ | ✅ | -
| DB 로드 | POST /api/:hostUid/database/load/:dbname | ✅ | ✅ | ✅ | 비동기 job
| DB 최적화 | POST /api/:hostUid/database/optimize/:dbname | ✅ | ✅ | ✅ | 비동기 job
| DB 검사 | POST /api/:hostUid/database/check/:dbname | ✅ | ✅ | ✅ | 비동기 job / repairdb 옵션
| DB 컴팩트 | POST /api/:hostUid/database/compact/:dbname | ✅ | ✅ | ✅ | 비동기 job
| 볼륨 추가 | POST /api/:hostUid/database/add-vol/:dbname | ✅ | ✅ | ✅ | 비동기 job
| 볼륨 추가 상태 | GET /api/:hostUid/database/add-vol-status/:dbname | ✅ | ✅ | -
| 트랜잭션 조회 | POST /api/:hostUid/database/transaction-info/:dbname | ✅ | ✅ | -
| 트랜잭션 종료 | POST /api/:hostUid/database/kill-transaction/:dbname | ✅ | ✅ | -
| 락 정보 조회 | POST /api/:hostUid/database/lock/:dbname | ✅ | ✅ | -
| 클래스 정보 조회 | POST /api/:hostUid/database/class-info/:dbname | ✅ | ✅ | -
DB 백업/복구 | 백업 실행 | POST /api/:hostUid/database/backup-db/:dbname | ✅ | ✅ | - | ⚠️ 동기 처리 — 장시간 시 timeout 위험
| 복구 실행 | POST /api/:hostUid/database/restore-db/:dbname | ✅ | ✅ | - | ⚠️ 동기 처리
| 백업 정보 조회 | GET /api/:hostUid/database/backup-db-info/:dbname | ✅ | ✅ | -
| 백업 목록 조회 | GET /api/:hostUid/database/backup-db-list/:dbname | ✅ | ✅ | -
| 자동 백업 스케줄 조회 | GET /api/:hostUid/database/backup-schedule/:dbname | ✅ | ✅ | -
| 자동 백업 스케줄 추가 | POST /api/:hostUid/database/backup-schedule/:dbname | ✅ | ✅ | -
| 자동 백업 스케줄 수정 | PUT /api/:hostUid/database/backup-schedule/:dbname | ✅ | ✅ | -
| 자동 백업 스케줄 삭제 | DELETE /api/:hostUid/database/backup-schedule/:dbname | ✅ | ✅ | -
| 자동 백업 오류 로그 | POST /api/:hostUid/database/auto-backup-db-err-log | ✅ | ✅ | -
DB 자동화 | 자동 시작 설정 | POST /api/:hostUid/database/auto-start/set | ✅ | ✅ | - | cubridconf [service] server 파라미터
| 자동 시작 해제 | POST /api/:hostUid/database/auto-start/remove | ✅ | ✅ | -
| 자동 볼륨 추가 조회 | GET /api/:hostUid/database/auto-add-vol/:dbname | ✅ | ✅ | -
| 자동 볼륨 추가 설정 | POST /api/:hostUid/database/auto-add-vol/:dbname | ✅ | ✅ | -
| 자동 볼륨 로그 | GET /api/:hostUid/database/auto-add-vol-log | ✅ | ✅ | -
| 자동 실행 쿼리 조회 | GET /api/:hostUid/database/auto-exec-query/:dbname | ✅ | ✅ | -
| 자동 실행 쿼리 설정 | POST /api/:hostUid/database/auto-exec-query/:dbname | ✅ | ✅ | -
| 자동 쿼리 오류 로그 | POST /api/:hostUid/database/auto-exec-query-err-log | ✅ | ✅ | -
DB 사용자 | 사용자 목록 조회 | GET /api/:hostUid/database/users/info/:dbname | ✅ | ✅ | -
| 사용자 생성 | POST /api/:hostUid/database/users | ✅ | ✅ | -
| 사용자 수정 | PUT /api/:hostUid/database/users/:dbname/:username | ✅ | ✅ | -
| 사용자 삭제 | DELETE /api/:hostUid/database/users/:dbname/:username | ✅ | ✅ | -
| DB 로그인 (직접) | POST /api/:hostUid/database/users/login/:dbname | ✅ | ✅ | -
| DB 로그인 (프로필) | POST /api/:hostUid/database/users/login-with-profile/:dbname | ✅ | ✅ | -
| DB 크기 조회 | GET /api/:hostUid/database/db-size/:dbname | ✅ | ✅ | -
브로커 | 브로커 목록 조회 | GET /api/:hostUid/broker/list | ✅ | ✅ | -
| 전체 브로커 시작 | POST /api/:hostUid/broker/start-all | ✅ | ✅ | - | CMS task: startbroker
| 전체 브로커 중지 | POST /api/:hostUid/broker/stop-all | ✅ | ✅ | - | CMS task: stopbroker
| 개별 브로커 시작 | POST /api/:hostUid/broker/start/:bname | ✅ | ✅ | -
| 개별 브로커 중지 | POST /api/:hostUid/broker/stop/:bname | ✅ | ✅ | -
| 개별 브로커 재시작 | POST /api/:hostUid/broker/restart/:bname | ✅ | ✅ | -
| 브로커 상태 조회 | GET /api/:hostUid/broker/status/:bname | ✅ | ✅ | -
| DBMT 사용자 추가 | POST /api/:hostUid/broker/dbmt-user | ✅ | ✅ | -
| DBMT 사용자 수정 | PUT /api/:hostUid/broker/dbmt-user | ✅ | ✅ | -
HA | 하트비트 목록 조회 | POST /api/:hostUid/ha/heartbeat-list | ✅ | ✅ | - | HA 노드 상태/역할
| HA 설정 재로드 | POST /api/:hostUid/ha/reload | ✅ | ✅ | -
| HA peer 자동 감지 | (CMS 로그인 시 자동) | ✅ | ✅ | - | 로그인 후 미등록 peer 제안
| HA peer 그룹 병합 제안 | (프론트 로직) | - | ✅ | - | 다른 그룹 peer 이동 제안
로그 | 브로커 로그 목록 | GET /api/:hostUid/log/broker/:bname | ✅ | ✅ | -
| DB 로그 목록 | GET /api/:hostUid/log/database/:dbname | ✅ | ✅ | -
| CMS 로그 목록 | GET /api/:hostUid/log/cms | ✅ | ✅ | -
| 관리자 로그 | GET /api/:hostUid/log/admin | ✅ | ✅ | -
| 로그 내용 조회 | POST /api/:hostUid/log/view | ✅ | ✅ | -
모니터링 | 호스트 리소스 통계 | GET /api/:hostUid/resource-monitoring/get-host-stat | ✅ | ✅ | -
| DB 공간 모니터링 | (start-info 기반) | ✅ | ✅ | -
| 볼륨 정보 모니터링 | (volume-info 기반) | ✅ | ✅ | -
CMS 설정 | 환경 정보 조회 | GET /api/:hostUid/cms-config/env | ✅ | ✅ | -
| 브로커 설정 조회 | GET /api/:hostUid/cms-config/broker-config/:confname | ✅ | ✅ | -
| 브로커 파라미터 설정 | POST /api/:hostUid/cms-config/broker-set-param | ✅ | ✅ | -
| 시스템 파라미터 조회 | GET /api/:hostUid/cms-config/all-sys-param | ✅ | ✅ | -
| 시스템 파라미터 설정 | POST /api/:hostUid/cms-config/set-sys-param | ✅ | ✅ | -
| 파라미터 덤프 | GET /api/:hostUid/cms-config/param-dump/:dbname | ✅ | ✅ | -
| 통계 덤프 | GET /api/:hostUid/cms-config/stat-dump/:dbname | ✅ | ✅ | -
| 쿼리 계획 덤프 | GET /api/:hostUid/cms-config/plan-dump/:dbname | ✅ | ✅ | -
CMS 사용자(DBMT) | DBMT 사용자 조회 | GET /api/:hostUid/cms-user | ✅ | ✅ | -
| DBMT 사용자 추가 | POST /api/:hostUid/cms-user | ✅ | ✅ | -
| DBMT 사용자 수정 | PUT /api/:hostUid/cms-user | ✅ | ✅ | -
| DBMT 사용자 삭제 | DELETE /api/:hostUid/cms-user/:targetid | ✅ | ✅ | -
| DBMT 암호 변경 | PUT /api/:hostUid/cms-user/set-password | ✅ | ✅ | -
비동기 작업(Job) | 활성 작업 목록 | GET /api/jobs/active | ✅ | ✅ | - | BackgroundJobsPanel에 표시
| 작업 상태 조회 | GET /api/jobs/:jobId | ✅ | ✅ | - | Adaptive polling (2s~30s)
파일 | 파일 존재 확인 | POST /api/:hostUid/file/checkfile | ✅ | - | - | 백엔드 내부 사용
배포/인프라 | 단일 서버 배포 (Node) | npm run build:server + start | ✅ | ✅ | - | NestJS가 정적파일 서빙
| pkg 실행파일 패키징 | npm run package:linux/windows/macos | ✅ | ✅ | - | Node.js 내장 단일 바이너리
| Electron 데스크톱 앱 | npm run package:electron | ✅ | ✅ | - | UDS 통신, app:// 프로토콜
| cwm.conf 설정 파일 | conf/cwm.conf | ✅ | - | - | PORT, SEED/SALT 자동생성, SSL 자동생성
| E2E 테스트 (Playwright) | npm run e2e:ui | - | ✅ | - | 104개 테스트, local-e2e/

## 요약
구분 | 항목 수 | 완료(BE+UI) | BE만 | UI만 | 미구현
인증 | 4 | 4 | 0 | 0 | 0
사용자 계정 | 5 | 5 | 0 | 0 | 0
호스트 관리 | 9 | 9 | 0 | 0 | 0
DB 라이프사이클 | 8 | 8 | 0 | 0 | 0
DB 관리 (비동기) | 14 | 14 | 0 | 0 | 0
DB 백업/복구 | 9 | 9 | 0 | 0 | 0
DB 자동화 | 8 | 8 | 0 | 0 | 0
DB 사용자 | 7 | 7 | 0 | 0 | 0
브로커 | 9 | 9 | 0 | 0 | 0
HA | 4 | 3 | 0 | 1 | 0
로그 | 5 | 5 | 0 | 0 | 0
모니터링 | 3 | 3 | 0 | 0 | 0
CMS 설정 | 8 | 8 | 0 | 0 | 0
CMS 사용자(DBMT) | 5 | 5 | 0 | 0 | 0
비동기 작업(Job) | 2 | 2 | 0 | 0 | 0
파일 | 1 | 0 | 1 | 0 | 0
배포/인프라 | 5 | 5 | 0 | 0 | 0

## 체크사항
우선순위 | 항목 | 내용 | 담당
🔴 High | backup/restore CmsJob 미통합 | backup-db, restore-db가 동기 HTTP로 처리됨. 대용량 DB 시 HTTP timeout 발생 가능. 다른 long-running op(optimize 등)과 달리 Job 패널에 표시 안 됨. | Backend
🔴 High | 실패 Job 재시도 UI 없음 | failed job에 dismiss만 가능. retry 버튼 없음. payload가 API 응답에 미포함. | Frontend
🟡 Medium | CI 테스트 스텝 | CI에 nx test 추가 완료. E2E는 실제 CUBRID 서버 필요로 CI 미포함. | Infra
🟡 Medium | CmsJobResult 타입 비일관성 | job type별 result 구조 다름(unload/compact/addvol/기타). unknown 타입으로 frontend 접근 시 런타임 오류 위험. | Backend
🟡 Medium | Electron /api prefix 호환 | infra/deployment의 setGlobalPrefix('api')가 CWM_DESKTOP=1 시 비활성화됨. Electron 브랜치 병합 시 toApiUpstreamPath 수정 필요. | Desktop
🟢 Low | purgeExpiredJobs 순차 처리 | 사용자/파일 이중 순차 루프. 다수 사용자 시 이벤트 루프 점유. Promise.allSettled 병렬화 가능. | Backend
🟢 Low | graceful shutdown 미구현 | server 종료 시 실행 중 runJob Promise 추적/대기 없음. 재시작 후 orphan recovery로 보완 중. | Backend
🟢 Low | E2E 테스트 셀렉터 검증 필요 | 기존 spec 파일의 UI 셀렉터가 현재 UI와 맞는지 실제 실행 확인 필요. | QA

## New UI
specification of web admin |  |  | Complexity Level: 1, 2, 3 Noted: Higher number is more complicated
Dec 10th, 2025
Development Team 1, CUBRID
@ Copyright 2025 CUBRID Corporation |  |  | UI Due Date = API Due Date + 1 Month
All right reserved
category | No. | feature | description | use of CM server | Question&Remark | priority | UI | API | Due(API) | Complete Date (Basic feature) | Complete Date (API) | Integration | Complexity UI | Complexity API |  | TestCase File (xls) reference | API URI | Note
WCA | 1 | Login | Login WCA service, JWT returned |  |  | High | Done | Done | 2025-12-01 | 2025-10-01 | 2025-10-01 | Done | 1 | 1
| 2 | Logout | Logout WCA service, old JWT is blacklisted |  |  | High | Done | Done | 2025-12-01 | 2025-10-02 | 2025-10-01 | Done | 1 | 1
| 3 | Change Password | Change password of WCA account. |  |  | Medium | Done | Done | 2025-12-01 | 2025-10-03 | 2025-10-01 | Done | 1 | 3
| 4 | Update User Info | Update User Information |  |  | High | Done | Done | 2026-01-01 | 2025-10-04 | 2025-10-01 | Done | 1 | 1
| 5 | Unregister | Unregister the WCA account and user file deleted. |  |  | High | Done | Done | 2026-01-01 | 2025-10-11 | 2025-10-01 | Done | 1 | 1
| 6 | Register | Register the WCA account and user file created and initialized. |  |  | High | Done | Done | 2026-01-01 | 2025-10-09 | 2025-10-01 | Done | 1 | 1
| 7 | Get service preference | Get preference (e.g., dashboard interval) for WCA service. |  |  | Medium | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 1 | 1
| 8 | Update dashboard Interval | Update the dashboard refresh interval. |  |  | High | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 2 | 1
| 9 | Update broker status interval | Update the broker status refresh interval. |  |  | High | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 2 | 1
top-file | 10 | 1, adding a host | * add VM-02 and confirm host registration at left side | no |  | High | Done | Done | 2026-01-01 | 2025-10-23 | 2025-11-01 | Done | 2 |  |  | No.1-CA top-file menu test scenario
| 11 | 2, change host info | * change VM-02 host to VM-01, confirm host registration at left side | no |  | High | Done | Done | 2026-01-01 | 2026-01-01 | 2025-11-01 | Done | 2 |  |  | No.1-CA top-file menu test scenario
| 12 | 3, export host info | * save the entered host information and check the information file | no |  | Low | Done | Done | 2026-06-01 | 2026-01-01 |  | Done | 1 | 1 | Compatibility with DCA | No.1-CA top-file menu test scenario
| 13 | 4, disconnect host connection | * disconnect host VM-01 connection and confirm result | yes |  | High | Done | X | 2026-01-01 | 2025-12-19 |  | Done | 3 | 2 |  | No.1-CA top-file menu test scenario
| 14 | 5, delete a host | * delete host VM-01, confirm host registration at left side | no |  | High | Done | Done | 2026-01-01 | 2025-12-12 | 2025-11-01 | Done | 3 | 2 |  | No.1-CA top-file menu test scenario
| 15 | 6, import host info | * get saved info from export VM-01 and check VM-01 result | no |  | Low | Done | Prepare | 2026-06-01 | 2026-01-01 |  | Prepare | 1 | 2 | Compatibility with DCA | No.1-CA top-file menu test scenario
| 16 | 7, connection | * connect host VM-01 and check demodb database status | yes |  | High | Done | Done | 2026-01-01 | 2025-12-05 | 2025-12-01 | Done | 3 | 2 |  | No.1-CA top-file menu test scenario
| 17 | 8, close current & all windows | * check status at right side after do close windows | no |  | High | Done | Done | 2026-01-01 |  |  | Done | 3 | 3 |  | No.1-CA top-file menu test scenario
| 18 | 9. user management | * 'admin' has the privileges of create/delete/modify user account. | no |  | Medium | Done | X | 2026-05-01 |  | 2025-03-01 | Progress | 2 | 2 |  | No.1-CA top-file menu test scenario
top-tools | 19 | 1, stop service | * stop host VM-01 service and check result | yes | Q: stop all running databases and brokers? when stop database, it will disapared in api. so when we want to start again. there is no database to start => CMS API includes stopped database in the list, i'll work on it | Medium | Done | X | 2026-04-01 | 2025-03-01 |  | Done | 1 | 1 | Is getallsysparam necessary? | No.2-CA top-tools menu test scenario
| 20 | 2, start service | * start VM-01 host service and check result | yes | Q: start all running databases and brokers? => yes | Medium | Done | X | 2026-04-01 | 2025-03-01 |  | Done | 1 | 1 | Is getallsysparam necessary? | No.2-CA top-tools menu test scenario
| 21 | 3, stop database | * stop demodb database & check result | yes | it has in database menu(right click). why should it is in top-tool? | Medium | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 3 | 3 |  | No.2-CA top-tools menu test scenario
| 22 | 4, start database | * start demodb dtabase & check result | yes |  | Medium | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 2 | 3 |  | No.2-CA top-tools menu test scenario
| 23 | 5, stop all brokers | * stop broker & check result | yes |  | Low | Done | Done | 2026-05-01 |  | 2026-03-01 | Progress | 1 | 1 |  | No.2-CA top-tools menu test scenario
| 24 | 6, start all brokers | * start broker & check result | yes |  | Low | Done | Done | 2026-05-01 |  | 2026-03-01 | Progress | 1 | 1 |  | No.2-CA top-tools menu test scenario
| 25 | 7, change password of admin | * change CA password and try login | yes |  | High | Done | Done | 2026-06-01 |  | 2026-02-01 | Progress | 2 | 1 |  | No.2-CA top-tools menu test scenario
| 26 | 8, add CMS users | * add a CA user and check result | yes |  | Medium | Done | Done | 2026-06-01 |  |  | Progress | 1 | 1 |  | No.2-CA top-tools menu test scenario
| 27 | 9, convert broker log to SQL | * copy and convert SQL log on Test Case and check result | yes |  | Low | Done | Prepare | 2026-02-01 | 2026-01-02 |  | Prepare | 1 | 3 | API : Transmit Log UI : Convert Log to SQL | No.2-CA top-tools menu test scenario
| 28 | 10, convert output of broker_log_top to excel to excel | * try with file TEST Data broker_log_top and check result | yes |  | Low | Done | Prepare | 2026-02-01 |  |  | Prepare | 3 | 3 |  | No.2-CA top-tools menu test scenario
| 29 | 11, service dashboard | * enable service dashboard and check output | yes |  | Medium | Done | Progress | 2026-01-01 |  |  | Prepare | 3 | 3 |  | No.2-CA top-tools menu test scenario
top-action | 30 | 1, show host dashboard | * close opened hashboard and do show host dashboard and check result | yes |  | High | Done | Progress | 2026-01-01 |  |  | Progress | 1 | 1 |  | No.3-CA top-action menu test scenario
| 31 | 2, server version | * check CUBRID server version | yes |  | High | Done | Done | 2026-01-01 | 2025-12-30 |  | ? | 2 | 1 |  | No.3-CA top-action menu test scenario
| 32 | 3-1, attribute-config parameter(DB) | * in parameter config, set service & server common parameters and check cubrid.conf | yes |  | High | Done | Done | 2026-01-01 |  |  | Prepare | 2 | 1 |  | No.3-CA top-action menu test scenario
| 33 | 3-2, attribute-config parameter(Broker) | * in parameter config, set broker parameters and check broker status | yes |  | High | Done | Prepare | 2026-01-01 |  | 2025-12-01 | Prepare | 3 | 1 |  | No.3-CA top-action menu test scenario
| 34 | 4-1, multi-host conf editor(DB) | * in multi-host conf editor, change environment value in server setting and check cubrid.conf | yes |  | High | Done | Done | X |  | 2025-12-01 | Progress | 1 | 1 | DB Config UI Missing | No.3-CA top-action menu test scenario
| 35 | 4-2, multi-host conf editor(Broker) | * in multi-host conf editor, change broker setting and confirm status of broker_new as OFF | yes |  | High | Done | Done | X |  | 2025-12-01 | Done | 3 | 1 |  | No.3-CA top-action menu test scenario
| 36 | 4-3, multi-host conf editor(Manager) | * in multi-host conf editor, change CM port and restart service and check connection to changed port | yes |  | High | Done | Done |  |  | 2025-12-01 | Prepare |  |  | Manager Config UI Missing | No.3-CA top-action menu test scenario
| 37 | 5-1, configuration parameter(DB) | * initialize DB parameter at configuration parameter and check result | yes |  | High | Done | Done |  |  | 2025-12-01 | Prepare |  |  | Right click -> Properties disabled | No.3-CA top-action menu test scenario
| 38 | 5-1, configuration parameter(Broker) | * initialize broker parameter at configuration parameter and check result | yes |  | High | Done | Done |  |  | 2025-12-01 | Prepare | 2 |  | Right click -> Properties no popup | No.3-CA top-action menu test scenario
| 39 | 5-1, configuration parameter(Manager) | * initialize manager parameter at configuration parameter and check result | yes |  | High | Done | Done |  |  | 2025-12-01 | Prepare | 2 |  |  | No.3-CA top-action menu test scenario
top-help | 40 | 1, help | * check display of help web page | no |  | High | Done | Done |  | 2025-12-24 |  | Done | 1 |  |  | No.4-CA top-help menu test scenario
| 41 | 3, report bug | * check connection to www.cubrid.com homepage | no |  | High | Done | X |  | 2025-12-25 |  | Done |  |  |  | No.4-CA top-help menu test scenario
| 42 | 3, CUBRID tools developments | * check connection to cubrid github page | no |  | High | Done | X |  | 2025-12-26 |  | Done |  |  |  | No.4-CA top-help menu test scenario
| 43 | 4, check for updates | * check update results | no |  | High | Done | X |  | 2025-12-27 |  | Done |  |  |  | No.4-CA top-help menu test scenario
| 44 | 5, server version | * confirm CUBRID DB Server version | yes |  | High | Done | X |  | 2025-12-28 |  | Done |  |  |  | No.4-CA top-help menu test scenario
| 45 | 6, About CUBRID admin | * confirm CUBRID admin version | no |  | High | Done | X |  | 2025-12-29 |  | Done |  |  |  | No.4-CA top-help menu test scenario
host-menu | 46 | 1, disconnect host and reconnect | * disconnect host connection VM-01 and reconnect, check results | yes |  | High | Done | X |  | 2025-12-30 |  | Done |  |  |  | No.5-CA host test scenario
| 47 | 2, add host | * refer No.1 top-file menu Test Case 1 | pass |  | Medium | Done | Done |  | 2026-01-04 | 2025-11-01 | Done | 1 |  |  | No.5-CA host test scenario
| 48 | 3, edit host | * refer No.1 top-file menu Test Case 2 | pass |  | High | Done | Done |  | 2026-01-03 | 2025-11-01 | Done |  |  |  | No.5-CA host test scenario
| 49 | 4, delete host | * refer No.1 top-file menu Test Case 4 | pass |  | High | Done | Done |  |  |  | Done |  |  |  | No.5-CA host test scenario
| 50 | 6, change manager's password | * refer No.2 top-tools menu Test Case 9 | pass |  | High | Done | Done | 2026-06-01 |  |  | Progress | 1 | 1 |  | No.5-CA host test scenario
database | 51 | 1, create database | * create new database and check results | yes |  | High | Done | Done | 2026-02-01 |  |  | Done | 3 | 3 |  | No.6-CA database and broker and log menu test scenario
| 52 | 2, properties | * refer top-action Test Case 3-1 | pass |  | High | Done | Done |  |  |  | Progress | 2 |  | Properties disabled | No.6-CA database and broker and log menu test scenario
broker (BR) | 53 | 3, properties | * remove add broker broker_new and check results | yes |  | Medium | Done | Done |  |  |  | Progress | 1 |  | Reusing the multi-conf | No.6-CA database and broker and log menu test scenario
| 54 | 4, show status | * execute show broker status and check info | yes |  | Low | done | Done |  |  |  | Done | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 55 | 5, bulk edit broker settings | * refer No.3 top-action Test Case 3-2 | pass |  | Low | done | Prepare |  |  |  | X | 1 |  | Cancelled | No.6-CA database and broker and log menu test scenario
| 56 | 6, stop all brokers & start | * stop all brokers and check broker status | yes |  | Low | done | Done |  |  |  | Progress | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 57 | 7-1, broker1(30000,RW)>broker stop & start | * select broker1, do stop and start and check results | yes |  | High | done | Done |  |  |  | Done | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 58 | 7-2, broker1(30000,RW)>status | * select show broker status broker1, and check results | yes |  | Low | done | Done |  |  |  | Done | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 59 | 7-3, broker1(30000,RW)>properties | * select broker1 properties and check info | yes |  | Medium | Done | Done |  |  |  | Done | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 60 | 7-4, broker1(30000,RW)>SQL Log | * output broker1 SQL Log | yes |  | High | Done | Done | 2026-01-01 | 2025-12-05 | 2026-01-01 | Done |  |  |  | No.6-CA database and broker and log menu test scenario
log | 61 | 8, Logs>Broker>access&error&admin Log | * select each broker log file and check output | yes |  | High | Done | Done | 2026-01-01 | 2025-12-06 | 2026-01-01 | Progress |  |  |  | No.6-CA database and broker and log menu test scenario
| 62 | 9, Logs>manager>access&error log | * select each manager log file and check output | yes |  | High | Done | Done | 2026-01-01 | 2025-12-07 | 2026-01-01 | Progress |  |  |  | No.6-CA database and broker and log menu test scenario
| 63 | 10, Logs>server>DB name>err log | * select error file for database DB name(demodb) and check output | yes |  | High | Done | Done | 2026-01-01 | 2025-12-23 | 2026-01-01 | Progress |  |  |  | No.6-CA database and broker and log menu test scenario
database - demodb | 64 | 1, logout/login | * login & logout to database demodb and check results | yes |  | High | Done | Done | 2026-01-01 | 2025-12-09 | 2026-01-01 | Done |  |  |  | No.7-CA database demodb-menu test scenario
| 65 | 3, open database dashboard | * open demodb dashboard and check results | yes |  | High | Done | Done | 2026-01-01 | 2025-12-19 | 2026-01-01 | Prepare |  |  |  | No.7-CA database demodb-menu test scenario
| 66 | 11, database stop/start | * stop/start demodb database and check results | yes |  | High | Done | Done | 2026-01-01 | 2025-12-18 | 2026-01-01 | Done |  |  |  | No.7-CA database demodb-menu test scenario
| 67 | 12, properties | * change demodb properties and check results | no |  | High | Done | Done | 2026-01-01 |  | 2026-01-01 | Prepare |  |  |  | No.7-CA database demodb-menu test scenario
demodb > management & info | 68 | 1, demodb>manage database->database unload | run demodb database unload and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 69 | 2, test_db>manage database>database load | run database load on test_db and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 70 | 3, demodb>manage database>database optimize | run database optimize on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 71 | 4, demodb>manage database>compact database | run compact database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 72 | 5, demodb>manage database>check database | * run check database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 73 | 6, demodb>manage database>copy database | * run copy database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 74 | 7, test_db>manage database>rename database | * rename test_db to test_db_rename and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 75 | 8, demodb>manage database>backup database | * run backup database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 76 | 9, demodb>manage database>restore database | * run restore database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 77 | 10, test_db_rename>manage database>delete database | * run delete database on test_db_rename and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 78 | 11, demodb>database info>lock information | * do database lock function on demodb and check results | yes |  | High | Done | Done | 2026-03-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 79 | 12, demodb>database info>transaction info | * run transaction info on demodb and check results | yes |  | High | Done | Done | 2026-03-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 80 | 13, demodb>database info>plan dump | * run plan cache function on demodb and check results | yes |  | High | Done | Done |  | 2026-01-02 | [5 empty] | No.8-CA database-demodb-management and information test scenario
| 81 | 14, demodb>database info>param dump | * run param dump on demodb and check results | yes |  | High | Done | Done |  | 2026-01-03 | [5 empty] | No.8-CA database-demodb-management and information test scenario
user | 82 | 2-1, create database user | * create database user and check results | no |  | High | Done | Done | 2026-05-01 |  |  |  | 2 | 3 |  | No.11-CA database-demodb-serial, user, trigger, procedure, synonym test scenario
user>test_user | 83 | 2-2, user>test_user>edit db user | * run menu edit db user and check results | no |  | High | Done | Done | 2026-05-01 |  |  |  | 1 | 2 |  | No.11-CA database-demodb-serial, user, trigger, procedure, synonym test scenario
| 84 | 2-3, user>test_user>drop db user | * run menu 'drop db user' and check results | no |  | High | Done | Done | 2026-05-01 |  |  |  | 1 | 2 |  | No.11-CA database-demodb-serial, user, trigger, procedure, synonym test scenario
job automation | 85 | 1-1, job automation>backup plan>add backup plan | * run 'add backup plan' and check results | yes |  | Medium | Done | Done | 2026-01-01 |  |  |  | 2 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 86 | 1-2, job automation>backup plan>auto backup log | * check auto backup log | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-12 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 87 | 1-3, job automation>query plan>add query plan | * run menu add query plan and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-13 | 2026-01-01 |  | 2 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 88 | 1-4, job automation>query plan>auto query log | * check auto query log | yes |  | Medium | Done | Done | 2026-01-01 |  | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
job automation> backup plan>full_back | 89 | 1-5, job automation>backup plan>demo_full_back>edit backup plan | * edit backup plan 'demo_full_back' and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-15 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 90 | 1-6, job automation>backup plan>demo_full_back>delete backup plan | * delete backup plan 'demo_full_back' and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-19 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
job automation> query plan>sql_test | 91 | 1-7, job automation>query plan>sql_test>edit query plan | * edit query plan 'sql_test' and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-19 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 92 | 1-8, job automation>query plan>sql_test>delete query plan | * delete query plan sql_test and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-20 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
database (DB) | 93 | 2-1, add volume | * run menu add volume and check results | yes |  | High | Done | Done | 2026-01-01 |  | 2026-02-01 |  | 1 | 3 |  | No.12-CA database-demodb-job automation, space test scenario
| 94 | 2-2, set automation volume | * set automation volume & check results | yes |  | High | Done | Done | 2026-01-01 |  |  |  | 1 | 1 |  | No.12-CA database-demodb-job automation, space test scenario |  | time set feature (define possible time interval) - max 2 if not in when duplicated
| 95 | 2-3, view database volume | * check database volume information | yes |  | Medium | Done | Done |  | 2026-01-22 | [5 empty] | No.12-CA database-demodb-job automation, space test scenario
HA | 96 | demodb(HA) -> stopdb |  |  |  | High | Done | Done
| 97 | demodb(HA) -> startdb |  |  |  | High | Done | Done
| 98 | heartbeat status |  |  |  | High | Done | Done
| 99 | heartbeat reload |  |  |  | High | Done | Done
| 100 | heartbeat list |  |  |  | High | Done | Done

## web admin spec
specification of web admin |  |  | Complexity Level: 1, 2, 3 Noted: Higher number is more complicated
Dec 10th, 2025
Development Team 1, CUBRID
@ Copyright 2025 CUBRID Corporation |  |  | UI Due Date = API Due Date + 1 Month
All right reserved
category | No. | feature | description | use of CM server | Question&Remark | priority | UI | API | Due(API) | Complete Date (Basic feature) | Complete Date (API) | Integration | Complexity UI | Complexity API |  | TestCase File (xls) reference | API URI | Note
WCA | 1 | Login | Login WCA service, JWT returned |  |  | High | Done | Done | 2025-12-01 | 2025-10-01 | 2025-10-01 | Done | 1 | 1
| 2 | Logout | Logout WCA service, old JWT is blacklisted |  |  | High | Done | Done | 2025-12-01 | 2025-10-02 | 2025-10-01 | Done | 1 | 1
| 3 | Change Password | Change password of WCA account. |  |  | Medium | Done | Done | 2025-12-01 | 2025-10-03 | 2025-10-01 | Done | 1 | 3
| 4 | Update User Info | Update User Information |  |  | High | Done | Done | 2026-01-01 | 2025-10-04 | 2025-10-01 | Done | 1 | 1
| 5 | Unregister | Unregister the WCA account and user file deleted. |  |  | High | Done | Done | 2026-01-01 | 2025-10-11 | 2025-10-01 | Done | 1 | 1
| 6 | Register | Register the WCA account and user file created and initialized. |  |  | High | Done | Done | 2026-01-01 | 2025-10-09 | 2025-10-01 | Done | 1 | 1
| 7 | Get service preference | Get preference (e.g., dashboard interval) for WCA service. |  |  | Medium | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 1 | 1
| 8 | Update dashboard Interval | Update the dashboard refresh interval. |  |  | High | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 2 | 1
| 9 | Update broker status interval | Update the broker status refresh interval. |  |  | High | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 2 | 1
top-file | 10 | 1, adding a host | * add VM-02 and confirm host registration at left side | no |  | High | Done | Done | 2026-01-01 | 2025-10-23 | 2025-11-01 | Done | 2 |  |  | No.1-CA top-file menu test scenario
| 11 | 2, change host info | * change VM-02 host to VM-01, confirm host registration at left side | no |  | High | Done | Done | 2026-01-01 | 2026-01-01 | 2025-11-01 | Done | 2 |  |  | No.1-CA top-file menu test scenario
| 12 | 3, export host info | * save the entered host information and check the information file | no |  | Low | Done | Done | 2026-06-01 | 2026-01-01 |  | Done | 1 | 1 | Compatibility with DCA | No.1-CA top-file menu test scenario
| 13 | 4, disconnect host connection | * disconnect host VM-01 connection and confirm result | yes |  | High | Done | X | 2026-01-01 | 2025-12-19 |  | Done | 3 | 2 |  | No.1-CA top-file menu test scenario
| 14 | 5, delete a host | * delete host VM-01, confirm host registration at left side | no |  | High | Done | Done | 2026-01-01 | 2025-12-12 | 2025-11-01 | Done | 3 | 2 |  | No.1-CA top-file menu test scenario
| 15 | 6, import host info | * get saved info from export VM-01 and check VM-01 result | no |  | Low | Done | Prepare | 2026-06-01 | 2026-01-01 |  | Prepare | 1 | 2 | Compatibility with DCA | No.1-CA top-file menu test scenario
| 16 | 7, connection | * connect host VM-01 and check demodb database status | yes |  | High | Done | Done | 2026-01-01 | 2025-12-05 | 2025-12-01 | Done | 3 | 2 |  | No.1-CA top-file menu test scenario
| 17 | 8, close current & all windows | * check status at right side after do close windows | no |  | High | Done | Done | 2026-01-01 |  |  | Done | 3 | 3 |  | No.1-CA top-file menu test scenario
| 18 | 9. user management | * 'admin' has the privileges of create/delete/modify user account. | no |  | Medium | Done | X | 2026-05-01 |  | 2025-03-01 | Progress | 2 | 2 |  | No.1-CA top-file menu test scenario
top-tools | 19 | 1, stop service | * stop host VM-01 service and check result | yes | Q: stop all running databases and brokers? when stop database, it will disapared in api. so when we want to start again. there is no database to start => CMS API includes stopped database in the list, i'll work on it | Medium | Done | X | 2026-04-01 | 2025-03-01 |  | Done | 1 | 1 | Is getallsysparam necessary? | No.2-CA top-tools menu test scenario
| 20 | 2, start service | * start VM-01 host service and check result | yes | Q: start all running databases and brokers? => yes | Medium | Done | X | 2026-04-01 | 2025-03-01 |  | Done | 1 | 1 | Is getallsysparam necessary? | No.2-CA top-tools menu test scenario
| 21 | 3, stop database | * stop demodb database & check result | yes | it has in database menu(right click). why should it is in top-tool? | Medium | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 3 | 3 |  | No.2-CA top-tools menu test scenario
| 22 | 4, start database | * start demodb dtabase & check result | yes |  | Medium | Done | Done | 2026-01-01 |  | 2025-12-01 | Done | 2 | 3 |  | No.2-CA top-tools menu test scenario
| 23 | 5, stop all brokers | * stop broker & check result | yes |  | Low | Done | Done | 2026-05-01 |  | 2026-03-01 | Progress | 1 | 1 |  | No.2-CA top-tools menu test scenario
| 24 | 6, start all brokers | * start broker & check result | yes |  | Low | Done | Done | 2026-05-01 |  | 2026-03-01 | Progress | 1 | 1 |  | No.2-CA top-tools menu test scenario
| 25 | 7, change password of admin | * change CA password and try login | yes |  | High | Done | Done | 2026-06-01 |  | 2026-02-01 | Progress | 2 | 1 |  | No.2-CA top-tools menu test scenario
| 26 | 8, add CMS users | * add a CA user and check result | yes |  | Medium | Done | Done | 2026-06-01 |  |  | Progress | 1 | 1 |  | No.2-CA top-tools menu test scenario
| 27 | 9, convert broker log to SQL | * copy and convert SQL log on Test Case and check result | yes |  | Low | Done | Prepare | 2026-02-01 | 2026-01-02 |  | Prepare | 1 | 3 | API : Transmit Log UI : Convert Log to SQL | No.2-CA top-tools menu test scenario
| 28 | 10, convert output of broker_log_top to excel to excel | * try with file TEST Data broker_log_top and check result | yes |  | Low | Prepare | Prepare | 2026-02-01 |  |  | Prepare | 3 | 3 |  | No.2-CA top-tools menu test scenario
| 29 | 11, service dashboard | * enable service dashboard and check output | yes |  | Medium | Prepare | Progress | 2026-01-01 |  |  | Prepare | 3 | 3 |  | No.2-CA top-tools menu test scenario
top-action | 30 | 1, show host dashboard | * close opened hashboard and do show host dashboard and check result | yes |  | High | Done | Progress | 2026-01-01 |  |  | Progress | 1 | 1 |  | No.3-CA top-action menu test scenario
| 31 | 2, server version | * check CUBRID server version | yes |  | High | Done | Done | 2026-01-01 | 2025-12-30 |  | ? | 2 | 1 |  | No.3-CA top-action menu test scenario
| 32 | 3-1, attribute-config parameter(DB) | * in parameter config, set service & server common parameters and check cubrid.conf | yes |  | High | Progress | Done | 2026-01-01 |  |  | Prepare | 2 | 1 |  | No.3-CA top-action menu test scenario
| 33 | 3-2, attribute-config parameter(Broker) | * in parameter config, set broker parameters and check broker status | yes |  | High | Progress | Prepare | 2026-01-01 |  | 2025-12-01 | Prepare | 3 | 1 |  | No.3-CA top-action menu test scenario
| 34 | 4-1, multi-host conf editor(DB) | * in multi-host conf editor, change environment value in server setting and check cubrid.conf | yes |  | High | Prepare | Done | X |  | 2025-12-01 | Progress | 1 | 1 | DB Config UI Missing | No.3-CA top-action menu test scenario
| 35 | 4-2, multi-host conf editor(Broker) | * in multi-host conf editor, change broker setting and confirm status of broker_new as OFF | yes |  | High | Done | Done | X |  | 2025-12-01 | Done | 3 | 1 |  | No.3-CA top-action menu test scenario
| 36 | 4-3, multi-host conf editor(Manager) | * in multi-host conf editor, change CM port and restart service and check connection to changed port | yes |  | High | Prepare | Done |  |  | 2025-12-01 | Prepare |  |  | Manager Config UI Missing | No.3-CA top-action menu test scenario
| 37 | 5-1, configuration parameter(DB) | * initialize DB parameter at configuration parameter and check result | yes |  | High | Prepare | Done |  |  | 2025-12-01 | Prepare |  |  | Right click -> Properties disabled | No.3-CA top-action menu test scenario
| 38 | 5-1, configuration parameter(Broker) | * initialize broker parameter at configuration parameter and check result | yes |  | High | Prepare | Done |  |  | 2025-12-01 | Prepare | 2 |  | Right click -> Properties no popup | No.3-CA top-action menu test scenario
| 39 | 5-1, configuration parameter(Manager) | * initialize manager parameter at configuration parameter and check result | yes |  | High | Prepare | Done |  |  | 2025-12-01 | Prepare | 2 |  |  | No.3-CA top-action menu test scenario
top-help | 40 | 1, help | * check display of help web page | no |  | High | Done | Done |  | 2025-12-24 |  | Done | 1 |  |  | No.4-CA top-help menu test scenario
| 41 | 3, report bug | * check connection to www.cubrid.com homepage | no |  | High | Done | X |  | 2025-12-25 |  | Done |  |  |  | No.4-CA top-help menu test scenario
| 42 | 3, CUBRID tools developments | * check connection to cubrid github page | no |  | High | Done | X |  | 2025-12-26 |  | Done |  |  |  | No.4-CA top-help menu test scenario
| 43 | 4, check for updates | * check update results | no |  | High | Done | X |  | 2025-12-27 |  | Done |  |  |  | No.4-CA top-help menu test scenario
| 44 | 5, server version | * confirm CUBRID DB Server version | yes |  | High | Done | X |  | 2025-12-28 |  | Done |  |  |  | No.4-CA top-help menu test scenario
| 45 | 6, About CUBRID admin | * confirm CUBRID admin version | no |  | High | Done | X |  | 2025-12-29 |  | Done |  |  |  | No.4-CA top-help menu test scenario
host-menu | 46 | 1, disconnect host and reconnect | * disconnect host connection VM-01 and reconnect, check results | yes |  | High | Done | X |  | 2025-12-30 |  | Done |  |  |  | No.5-CA host test scenario
| 47 | 2, add host | * refer No.1 top-file menu Test Case 1 | pass |  | Medium | Done | Done |  | 2026-01-04 | 2025-11-01 | Done | 1 |  |  | No.5-CA host test scenario
| 48 | 3, edit host | * refer No.1 top-file menu Test Case 2 | pass |  | High | Done | Done |  | 2026-01-03 | 2025-11-01 | Done |  |  |  | No.5-CA host test scenario
| 49 | 4, delete host | * refer No.1 top-file menu Test Case 4 | pass |  | High | Done | Done |  |  |  | Done |  |  |  | No.5-CA host test scenario
| 50 | 6, change manager's password | * refer No.2 top-tools menu Test Case 9 | pass |  | High | Done | Done | 2026-06-01 |  |  | Progress | 1 | 1 |  | No.5-CA host test scenario
database | 51 | 1, create database | * create new database and check results | yes |  | High | Done | Done | 2026-02-01 |  |  | Done | 3 | 3 |  | No.6-CA database and broker and log menu test scenario
| 52 | 2, properties | * refer top-action Test Case 3-1 | pass |  | High | Prepare | Done |  |  |  | Progress | 2 |  | Properties disabled | No.6-CA database and broker and log menu test scenario
broker (BR) | 53 | 3, properties | * remove add broker broker_new and check results | yes |  | Medium | Prepare | Done |  |  |  | Progress | 1 |  | Reusing the multi-conf | No.6-CA database and broker and log menu test scenario
| 54 | 4, show status | * execute show broker status and check info | yes |  | Low | done | Done |  |  |  | Done | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 55 | 5, bulk edit broker settings | * refer No.3 top-action Test Case 3-2 | pass |  | Low | done | Prepare |  |  |  | X | 1 |  | Cancelled | No.6-CA database and broker and log menu test scenario
| 56 | 6, stop all brokers & start | * stop all brokers and check broker status | yes |  | Low | done | Done |  |  |  | Progress | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 57 | 7-1, broker1(30000,RW)>broker stop & start | * select broker1, do stop and start and check results | yes |  | High | done | Done |  |  |  | Done | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 58 | 7-2, broker1(30000,RW)>status | * select show broker status broker1, and check results | yes |  | Low | done | Done |  |  |  | Done | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 59 | 7-3, broker1(30000,RW)>properties | * select broker1 properties and check info | yes |  | Medium | Done | Done |  |  |  | Done | 1 |  |  | No.6-CA database and broker and log menu test scenario
| 60 | 7-4, broker1(30000,RW)>SQL Log | * output broker1 SQL Log | yes |  | High | Done | Done | 2026-01-01 | 2025-12-05 | 2026-01-01 | Done |  |  |  | No.6-CA database and broker and log menu test scenario
log | 61 | 8, Logs>Broker>access&error&admin Log | * select each broker log file and check output | yes |  | High | Done | Done | 2026-01-01 | 2025-12-06 | 2026-01-01 | Progress |  |  |  | No.6-CA database and broker and log menu test scenario
| 62 | 9, Logs>manager>access&error log | * select each manager log file and check output | yes |  | High | Done | Done | 2026-01-01 | 2025-12-07 | 2026-01-01 | Progress |  |  |  | No.6-CA database and broker and log menu test scenario
| 63 | 10, Logs>server>DB name>err log | * select error file for database DB name(demodb) and check output | yes |  | High | Done | Done | 2026-01-01 | 2025-12-23 | 2026-01-01 | Progress |  |  |  | No.6-CA database and broker and log menu test scenario
database - demodb | 64 | 1, logout/login | * login & logout to database demodb and check results | yes |  | High | Done | Done | 2026-01-01 | 2025-12-09 | 2026-01-01 | Done |  |  |  | No.7-CA database demodb-menu test scenario
| 65 | 3, open database dashboard | * open demodb dashboard and check results | yes |  | High | Prepare | Done | 2026-01-01 | 2025-12-19 | 2026-01-01 | Prepare |  |  |  | No.7-CA database demodb-menu test scenario
| 66 | 11, database stop/start | * stop/start demodb database and check results | yes |  | High | Done | Done | 2026-01-01 | 2025-12-18 | 2026-01-01 | Done |  |  |  | No.7-CA database demodb-menu test scenario
| 67 | 12, properties | * change demodb properties and check results | no |  | High | Progress | Done | 2026-01-01 |  | 2026-01-01 | Prepare |  |  |  | No.7-CA database demodb-menu test scenario
demodb > management & info | 68 | 1, demodb>manage database->database unload | run demodb database unload and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 69 | 2, test_db>manage database>database load | run database load on test_db and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 70 | 3, demodb>manage database>database optimize | run database optimize on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 71 | 4, demodb>manage database>compact database | run compact database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 72 | 5, demodb>manage database>check database | * run check database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  | 2026-02-01 |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 73 | 6, demodb>manage database>copy database | * run copy database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 74 | 7, test_db>manage database>rename database | * rename test_db to test_db_rename and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 75 | 8, demodb>manage database>backup database | * run backup database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 76 | 9, demodb>manage database>restore database | * run restore database on demodb and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 77 | 10, test_db_rename>manage database>delete database | * run delete database on test_db_rename and check results | yes |  | High | Done | Done | 2026-02-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 78 | 11, demodb>database info>lock information | * do database lock function on demodb and check results | yes |  | High | Done | Done | 2026-03-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 79 | 12, demodb>database info>transaction info | * run transaction info on demodb and check results | yes |  | High | Done | Done | 2026-03-01 |  |  |  | 3 | 3 |  | No.8-CA database-demodb-management and information test scenario
| 80 | 13, demodb>database info>plan dump | * run plan cache function on demodb and check results | yes |  | High | Done | Done |  | 2026-01-02 | [5 empty] | No.8-CA database-demodb-management and information test scenario
| 81 | 14, demodb>database info>param dump | * run param dump on demodb and check results | yes |  | High | Done | Done |  | 2026-01-03 | [5 empty] | No.8-CA database-demodb-management and information test scenario
user | 82 | 2-1, create database user | * create database user and check results | no |  | High | Done | Done | 2026-05-01 |  |  |  | 2 | 3 |  | No.11-CA database-demodb-serial, user, trigger, procedure, synonym test scenario
user>test_user | 83 | 2-2, user>test_user>edit db user | * run menu edit db user and check results | no |  | High | Done | Done | 2026-05-01 |  |  |  | 1 | 2 |  | No.11-CA database-demodb-serial, user, trigger, procedure, synonym test scenario
| 84 | 2-3, user>test_user>drop db user | * run menu 'drop db user' and check results | no |  | High | Done | Done | 2026-05-01 |  |  |  | 1 | 2 |  | No.11-CA database-demodb-serial, user, trigger, procedure, synonym test scenario
job automation | 85 | 1-1, job automation>backup plan>add backup plan | * run 'add backup plan' and check results | yes |  | Medium | Done | Done | 2026-01-01 |  |  |  | 2 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 86 | 1-2, job automation>backup plan>auto backup log | * check auto backup log | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-12 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 87 | 1-3, job automation>query plan>add query plan | * run menu add query plan and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-13 | 2026-01-01 |  | 2 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 88 | 1-4, job automation>query plan>auto query log | * check auto query log | yes |  | Medium | Done | Done | 2026-01-01 |  | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
job automation> backup plan>full_back | 89 | 1-5, job automation>backup plan>demo_full_back>edit backup plan | * edit backup plan 'demo_full_back' and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-15 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 90 | 1-6, job automation>backup plan>demo_full_back>delete backup plan | * delete backup plan 'demo_full_back' and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-19 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
job automation> query plan>sql_test | 91 | 1-7, job automation>query plan>sql_test>edit query plan | * edit query plan 'sql_test' and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-19 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
| 92 | 1-8, job automation>query plan>sql_test>delete query plan | * delete query plan sql_test and check results | yes |  | Medium | Done | Done | 2026-01-01 | 2026-01-20 | 2026-01-01 |  | 1 | 2 |  | No.12-CA database-demodb-job automation, space test scenario
database (DB) | 93 | 2-1, add volume | * run menu add volume and check results | yes |  | High | Done | Done | 2026-01-01 |  | 2026-02-01 |  | 1 | 3 |  | No.12-CA database-demodb-job automation, space test scenario
| 94 | 2-2, set automation volume | * set automation volume & check results | yes |  | High | Done | Done | 2026-01-01 |  |  |  | 1 | 1 |  | No.12-CA database-demodb-job automation, space test scenario |  | time set feature (define possible time interval) - max 2 if not in when duplicated
| 95 | 2-3, view database volume | * check database volume information | yes |  | Medium | Done | Done |  | 2026-01-22 | [5 empty] | No.12-CA database-demodb-job automation, space test scenario
HA | 96 | 96 |  |  |  | High | ? | Prepare
| 97 | 97 |  |  |  | High | ? | Prepare
| 98 | 98 |  |  |  | High | ? | Prepare
| 99 | 99 |  |  |  | High | ? | Prepare
| 100 | 100 |  |  |  | High | ? | Prepare

## Timeline
기간 |  | API (UI = API + 1 Month) | Electorn | Unit Test | QA
2025-12-22 | 2025-12-26 | 7, 8, 9, 29, 56
2025-12-29 | 2026-01-02
2026-01-05 | 2026-01-09 | 85, 86, 87, 88
2026-01-12 | 2026-01-16 | 89, 90, 91, 92
2026-01-19 | 2026-01-23 | 51
2026-01-26 | 2026-01-30 | 68, 69
2026-02-02 | 2026-02-06 | 51(기능개선), 69(지연)
2026-02-09 | 2026-02-13
2026-02-16 | 2026-02-20
2026-02-23 | 2026-02-27
2026-03-02 | 2026-03-06
2026-03-09 | 2026-03-13
2026-03-16 | 2026-03-20
2026-03-23 | 2026-03-27
2026-03-30 | 2026-04-03
2026-04-06 | 2026-04-10
2026-04-13 | 2026-04-17
2026-04-20 | 2026-04-24
2026-04-27 | 2026-05-01
2026-05-04 | 2026-05-08
2026-05-11 | 2026-05-15
2026-05-18 | 2026-05-22
2026-05-25 | 2026-05-29
2026-06-01 | 2026-06-05 |  | V
2026-06-08 | 2026-06-12 |  | V
2026-06-15 | 2026-06-19 |  | V
2026-06-22 | 2026-06-26 |  | V
2026-06-29 | 2026-07-03 |  | V
2026-07-06 | 2026-07-10 |  | V
2026-07-13 | 2026-07-17 |  | V
2026-07-20 | 2026-07-24 |  | V
2026-07-27 | 2026-07-31 |  | V
2026-08-03 | 2026-08-07 |  | V
2026-08-10 | 2026-08-14 |  | V
2026-08-17 | 2026-08-21 |  | V
2026-08-24 | 2026-08-28 |  | V
2026-08-31 | 2026-09-04 |  | V
2026-09-07 | 2026-09-11 |  |  | V
2026-09-14 | 2026-09-18 |  |  | V
2026-09-21 | 2026-09-25 |  |  | V
2026-09-28 | 2026-10-02 |  |  | V
2026-10-05 | 2026-10-09 |  |  | V
2026-10-12 | 2026-10-16 |  |  | V
2026-10-19 | 2026-10-23 |  |  | V
2026-10-26 | 2026-10-30 |  |  | V
2026-11-02 | 2026-11-06 |  |  |  | V
2026-11-09 | 2026-11-13 |  |  |  | V
2026-11-16 | 2026-11-20 |  |  |  | V
2026-11-23 | 2026-11-27 |  |  |  | V
2026-11-30 | 2026-12-04 |  |  |  | V
2026-12-07 | 2026-12-11 |  |  |  | V
2026-12-14 | 2026-12-18 |  |  |  | V
2026-12-21 | 2026-12-25 |  |  |  | V

## Sheet1
기간 (주차) | API (백엔드 서버) - 이건중 | 프론트엔드 (UI) - Rathana
20260309-20260313 | TOOLS-4855 : 코드 리팩토링 및 URI 수정 등 변경사항 적용 (TOOLS-4855 Implementation 6번 - 9번) TOOLS-4847 : 브로커 전체 시작 / 정지 API 2종 TOOLS-4858 : 데이터베이스 사용자 관리 API 5종 TOOLS-4861 : CMS 사용자 관리 API 4종 | Google Antigravity + Stitch 이용한 신 UI 개발 연구 신규 UI 적용한 데모 구현
20260316-20260320 | TOOLS-4861 : CMS 사용자 관리 API 4종 (수정, 누락 API 추가) TOOLS-4869 : backupdb API 2종 TOOLS-4870 : get/set broker conf API 2종 TOOLS-4871 : getdbsize, copydb API 2종 TOOLS-4873 : getbakcuplist, restoredb API 2종 | UI 개선 (색상 변경) 기존 API 재 통합 시스템 매트릭 구현 backup plan 날짜 설정에 추가적인 설정 (주간, 주말, etc.) config 편집시 UI UX 개선 로그 pagination
20260323-20260327 | - 에러 처리 개선 및 단순화 * note에 CMS 에러메세지 전달 * 기존 도메인별 에러 제거 및 CMS 에러로 통합 - HA 기능 구현 * heartbeat list - 배포 관련 인증서 해결법 조사 * reverse proxy 적용하여 클라이언트 접속시 1회 신뢰시 서비스 이용 가능한 구조로 배포 (예정) - 서비스 Issue (문제점 및 버그) web manager spec 문서 별도 시트에 명시 | - 신규 UI 개선 및 통합 작업 * Interval 버튼 대시보드 내에 추가 * 신규 UI 깃허브 업로드 예정 * 심볼컬러 변경, UI 크기 조정, 그래프 디자인 개선 등 전반적인 디자인 세부사항 수정 * 대시보드 내에 Synchronization 버튼 추가
20260330-20260403 | TOOLS-4877 - HA 기능 구현, HA 여부 판별 로직 삽입, 유틸리티 추가, 코드 정리 TOOLS-4879 - 응답 메시지 통일, createdb 버그 추정 Web manager 디버깅 | - TOOLS-4880 : UI 현대화 * 대시보드 interval 버튼 UI 개선 * log 출력 기능 개선 (페이지네이션 적용) * log에서 sql 추출기능 * top log excel기능

## Issues
No. | Type | AS-IS | TO-BE | Create Date | Resolved Date | IsDone
1 | Front | When 'login to host' fails, it doesn't roll back the process and freeze. | If dbmtuserlogin fails, it should rollback (e.g. turn off display tab, etc.) |  |  | Done
2 | Front | Error message is retrieved from the 'title' of error response. | Error message for user should be retrieved from 'note' of error response |  |  | Done
3 | Front | Refresh (F5) initializes the state and closes all tabs and reset the connection | Refresh (F5) should be customized so it doesn't reset the state (tabs, connections, etc.) |  |  | Done
4 | Deploy | Frontend and backend deployed on different address and port | Reverse proxy has to be applied and both frontend and backend has to be deployed using same address and port
5 | Server | HA is not considered in business logic | HA should be covered in business logic and algorithm for HA should be implemented
6 | Deploy | User has to execute frontend and backend by manually usind 'node' command and parameters | Installation should be done via shell / executable
7 | Deploy | Ambiguous method of managing critical information (SEED, SALT) and data | Strategy for managing critical data / information for service should be decided. (e.g. .env file)
8 | Server | Faiure of host login returns 'success' on note | Message for failure of login must return note : faiilure message with http status code '401'
9 | Front | Clicking host after failing login doesn't retry the login | Whenever user clicks the host, it should refresh / relogin based on state |  |  | Done
10 | Front | DB login cannot handle empty password | empty password should be allowed as input |  |  | Done
11 | Server | Token still remains even when cms login failed | token has to be removed when cms login failed | 2026-04-02
12 | Front | Host data remains even after failing cms login | slice / state has to be initialized if cms login fails | 2026-04-02 |  | Done
13 | Front | Right click on host displays 'Disconnect' when user is not logged into server | Right click menu has to display 'Connect' when user is not logged into server | 2026-04-02 |  | Done
14 | Front | Service Dashboard sends request with faulty url (https://{address}/[object%20object].... | URL should be fixed | 2026-04-02 |  | Done
15 | Front | Right click on empty space of navigation bar on left side display default browser menu | Right click on empty space of navigation bar should display the web manager menu | 2026-04-02
16 | Front | When user closes createdb dialog and reopen it, still the previous information remains | Createdb dialog should be initialized when ever it is closed | 2026-04-02 |  | Done
17 | Front | After successfully terminating createdb, db list is not refreshed | After createdb, start-info should be invoked / rv from createdb should be applied on db list | 2026-04-02 |  | Done
18 | Front | User cannot see full path of createdb, etc. | Shortened / Hidden full path should be shown when user clicks ... / full path should be displayed with hovering text box | 2026-04-02 |  | Done
19 | Front | clicking on table creates the dashboard window | clicking on table has to do nothing or just open modal with table(class) info | 2026-04-02 |  | Done
20 | Front | Deletedb doesn't work and display 'Spinner is not defined' instead | deletedb should work | 2026-04-02 |  | Done
21 | Server | DB Profile / login action is ambiguous | save db profile and db login action has to be more clear | 2026-04-02
22 | Front | After Registration,
| Front | create db: add external volume, auto expansion, over view page. it display data, temp as volume purpose. | all volume purpose should change permanent. | 2026-05-21 | 2026-05-22 | Done
| Front | Service Dashboard: address always localhost | it should dyamic based on user created | 2026-05-21 | 2026-05-22 | Done
| Front | Add server grouping for HA-related nodes Introduce a group concept for servers to group related HA nodes. Reflect grouping in: Service Dashboard Server Navigator |  |  |  | Done
| Front | Broker Dashbaord Basic Infomation | It should display information related to broker |  | 2026-05-28 | Done
| Front | Shortcut key, Ctrl + R | Refresh page data like F5 |  | 2026-05-28 | Done
| Front | Shortcut key, Ctrl + W | close current tab, |  |  | Progress